## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## SAMPLE
An Amazing UOW Short Course
Vice-Chancellor's Unit
Patricia Davidson
Project start date: | 2022-01-31 | [10 empty] | Scrolling increment: | [5 empty] | 0
Milestone marker: | 1 | 1 |  |  | January | [6 empty] | February | [27 empty] | March
 | time axis 2022-01-31 to 2022-03-27
Milestone description | Assigned to | Progress | Start | Days | time axis 2022-01-31 to 2022-03-27
Module 1 | Patricia/LTC |  | 2022-02-15 | 1 | bar: 2022-02-15
Write module outcomes | Ross | 100% | 2022-01-31 | 3
Write/source module content | Ross | 75% | 2022-01-31 | 3
Write module activities | Ross | 50% | 2022-01-31 | 4
Complete module planner for module 1 | Ross | 75% | 2022-01-31 | 5
Build Content in platform | LTC | 10% | 2022-02-07 | 5
Review Built Module | Ross | 0% | 2022-02-13 | 2
Module Signoff | Ross/LTC | 0% | 2022-02-14 | 2
Module 2
Task 1 |  | 0% |  | 2
Task 2 |  | 0%
Task 3 |  | 0%
Task 4
Task 5
Module 3
Task 1 |  |  | 2022-03-25 | 4
Task 2 |  |  | 2022-03-29 | 14
Task 3 |  |  | 2022-04-14 | 6
Task 4 |  |  | 2022-04-27 | 3
Task 5 |  |  | 2022-04-19 | 19
Module 4
Task 1 |  |  | 2022-04-16 | 15
Task 2 |  |  | 2022-04-08 | 5
Task 3 |  |  | 2022-05-29 | 5
Task 4
Task 5
Project Deadline |  |  | 2022-03-11 | 1 | bar: 2022-03-11
To add more data, Insert new rows ABOVE this one

## Green
Project title
School/Unit Name
Project lead
Project start date: | 2022-02-25 | [10 empty] | Scrolling increment: | [5 empty] | 0
Milestone marker: | 1 | 1 |  |  | February | [6 empty] | March | [27 empty] | April
 | time axis 2022-02-25 to 2022-04-21
Milestone description | Assigned to | Progress | Start | Days | time axis 2022-02-25 to 2022-04-21
Title 1
Task 1 |  | 30% | 2022-03-10 | 3
Task 2 |  | 1% | 2022-03-15 | 1 | bar: 2022-03-15
Task 3 |  | 50% | 2022-03-07 | 10
Task 4 |  | 2% | 2022-03-30 | 1 | bar: 2022-03-30
Task 5 |  | 10% | 2022-03-16 | 6
Title 2
Task 1 |  | 60% | 2022-03-16 | 13
Task 2 |  | 50% | 2022-03-17 | 9
Task 3 |  | 33% | 2022-03-25 | 11
Task 4 |  |  | 2022-04-03 | 1 | bar: 2022-04-03
Task 5 |  |  | 2022-04-04 | 24
Title 3
Task 1 |  |  | 2022-03-25 | 4
Task 2 |  |  | 2022-03-29 | 14
Task 3 |  |  | 2022-04-14 | 6
Task 4 |  |  | 2022-04-27 | 3
Task 5 |  |  | 2022-04-19 | 19
Title 4
Task 1 |  |  | 2022-04-16 | 15
Task 2 |  |  | 2022-04-08 | 5
Task 3 |  |  | 2022-05-29 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Blue
Project title
School/Unit Name
Project lead
Project start date: | 2022-03-03 | [10 empty] | Scrolling increment: | [5 empty] | 0
Milestone marker: | 1 | 1 |  |  | March | [34 empty] | April
 | time axis 2022-03-03 to 2022-04-27
Milestone description | Assigned to | Progress | Start | Days | time axis 2022-03-03 to 2022-04-27
Title 1
Task 1 |  | 25% | 2022-03-10 | 3
Task 2 |  |  | 2022-03-15 | 1 | bar: 2022-03-15
Task 3 |  | 50% | 2022-03-07 | 10
Task 4 |  |  | 2022-03-30 | 1 | bar: 2022-03-30
Task 5 |  | 10% | 2022-03-16 | 6
Title 2
Task 1 |  | 60% | 2022-03-16 | 13
Task 2 |  | 50% | 2022-03-17 | 9
Task 3 |  | 33% | 2022-03-25 | 11
Task 4 |  |  | 2022-04-03 | 1 | bar: 2022-04-03
Task 5 |  |  | 2022-04-04 | 24
Title 3
Task 1 |  |  | 2022-03-25 | 4
Task 2 |  |  | 2022-03-29 | 14
Task 3 |  |  | 2022-04-14 | 6
Task 4 |  |  | 2022-04-27 | 3
Task 5 |  |  | 2022-04-19 | 19
Title 4
Task 1 |  |  | 2022-04-16 | 15
Task 2 |  |  | 2022-04-08 | 5
Task 3 |  |  | 2022-05-29 | 5
Task 4
Task 5
Project Deadline |  |  | 2022-03-03 | 1 | bar: 2022-03-03
To add more data, Insert new rows ABOVE this one

## Purple
Project title
School/Unit Name
Project lead
Project start date: | 2022-03-03 | [10 empty] | Scrolling increment: | [5 empty] | 0
Milestone marker: | 1 | 1 |  |  | March | [34 empty] | April
 | time axis 2022-03-03 to 2022-04-27
Milestone description | Assigned to | Progress | Start | Days | time axis 2022-03-03 to 2022-04-27
Title 1
Task 1 |  | 25% | 2022-03-10 | 3
Task 2 |  |  | 2022-03-15 | 1 | bar: 2022-03-15
Task 3 |  | 50% | 2022-03-07 | 10
Task 4 |  |  | 2022-03-30 | 1 | bar: 2022-03-30
Task 5 |  | 10% | 2022-03-16 | 6
Title 2
Task 1 |  | 60% | 2022-03-16 | 13
Task 2 |  | 50% | 2022-03-17 | 9
Task 3 |  | 33% | 2022-03-25 | 11
Task 4 |  |  | 2022-04-03 | 1 | bar: 2022-04-03
Task 5 |  |  | 2022-04-04 | 24
Title 3
Task 1 |  |  | 2022-03-25 | 4
Task 2 |  |  | 2022-03-29 | 14
Task 3 |  |  | 2022-04-14 | 6
Task 4 |  |  | 2022-04-27 | 3
Task 5 |  |  | 2022-04-19 | 19
Title 4
Task 1 |  |  | 2022-04-16 | 15
Task 2 |  |  | 2022-04-08 | 5
Task 3 |  |  | 2022-05-29 | 5
Task 4
Task 5
Project Deadline |  |  | 2022-03-03 | 1 | bar: 2022-03-03
To add more data, Insert new rows ABOVE this one